## Sheet1
Task | Start | End | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Proposal | Week 1 | Week 4 | 4 Weeks
Planning
Initial Idea's - Understanding challenge brief | Week 1 | Week 2 | 2 Weeks
Aesthetic & Colour Palette | Week 1 | Week 3 | 3 Weeks
Narrative creation | Week 1 | Week 3 | 3 Weeks
StoryBoarding & Sketches | Week 2 | Week 4 | 3 Weeks
Research
Cinema 4D research | Week 1 | Week 7 | 7 Weeks
Lighting | Week 1 | Week 2 | 2 Weeks
Rendering | Week 2 | Week 3 | 2 Weeks
Texturing & Materials | Week 3 | Week 4 | 2 Weeks
Effectors | Week 4 | Week 5 | 2 Weeks
X-Particles research | Week 5 | Week 7 | 3 Weeks
Particle Control | Week 5 | Week 6 | 2 Weeks
Particle Effectors | Week 6 | Week 7 | 2 Weeks
Book research | Week 4 | Week 6 | 3 Weeks
Software Justification | Week 2 | Week 3 | 2 Weeks
Development
Testing | Week 4 | Week 7 | 4 Weeks
Scene & Object developments | Week 5 | Week 12 | 8 Weeks
Project To Do's | Week 6 | Week 12 | 7 Weeks
Rendering Time | Week 9 | Wee 11 | 3 Weeks
Editing & Motion Tracking (After Effects CC) | Week 10 | Week 11 | 2 Weeks
Exporting & Uploading to Vimeo | Week 11 | Week 11 | 1 Week
Reflection
Project Feedback - Presenting animation to target audience | Week 12 | Week 13 | 2 Weeks
Collecting & Analysing feedback | Week 12 | Week 13 | 2 Weeks
Reflection on the feedback and further improvements | Week 12 | Week 13 | 2 Weeks
Personal Reflection | Week 12 | Week 13 | 2 Weeks
Critical Reflection | Week 12 | Week 13 | 2 Weeks